## PreCAB (hidden)
RFC # | TITLE | TYPE | DESCRIPTION AND JUSTIFICATION | IMPLEMENTING TEAM | Change Requestor | IMPACT | Risk Level | REQUEST TARGET DATE | REMARKS | Discussion During PreCAB | Month | RFC # | TITLE | URGENCY | TYPE | SCOPE | NATURE | SYSTEM | DESCRIPTION AND JUSTIFICATION | PRE-CAB DATE | CHANGE REQUESTOR | BY IMPLEMENTING TEAM (Specific) | IMPLEMENTING TEAM | IMPACT | REQUEST TARGET DATE | Endorsement REMARKS | *SIDE NOTES | RFCSTATUS | PIE UPLOADED IN CITSM | BACKOUT PLAN | CURRENT CITSM STATUS | OATC STATUS | RELEASE CHECKLIST | CHANGE PLAN | MOP ATTACHED | By Change Owner | IMPLEMENTED WITH Concerns (SA/NSA) | By Team (Unauthorized, Emergency) | Change with Service Downtime (Yes/No?) | SYSTEM (Specific) | EXTENDED Service DOWNTIME (*of the Change) | IR Ticket Number | WITH IR? | IR LEVEL | Issue description | RCA | ACTION PERFORMED | PIE CATEGORIZATION | PEOPLE, PROCESS, PRODUCT, PARTNER | ISSUE SOURCE | Preventive Actions | Control | Control Reason based on Issue description | 5 WHYS | Other Info | ABC | Expedited Reason | Project / BAU | Parent RFC | Related to a previous RFC? | Rework?
RFC629598 | CXE Release 5B - 5.1.0 | CXE - Application, Modification | #REF! | #REF! | #REF! | #REF! | MEDIUM | #REF! | BAU Driven | <Free text> |  | RFC629598 | #REF! |  | #REF! |  | #REF! | #REF! | #REF! |  | #REF! |  | #REF! | #REF! | #REF! | [10 empty] | #REF! |  |  | #REF! | #REF!
Change Plan Tab | #REF!
Children RFCs Tab | Incomplete
A) Change Details | #REF!
RFC Number | 1
Target Implementation Date | 0
RFC Title | 1
Change Owner | #REF!
Change Owner Group | #REF!
Approved by | #REF!
System Name | 1
Change Type | 1
Related to Fix | 1
Project/BAU | 1
B) Risk Calculator | INC
C) Change General Info | #REF!
Change Requestor | #REF!
Change Requestor CIT | #REF!
Change Requestor Group | #REF!
BG & Justification | #REF!
Scope | #REF!
Benefits | #REF!
Business Owner / PCT | 0 | Req. if Appl.
Supporting Team | 0
D) Risk Mngmt. (If High Only) | OK
Risk Event | 1
Impact | 1
Probability | 1
Action | 1
Response | 1
Owner | 1
Do not modify | #REF!

## Table (hidden)
Application-Configuration | 1 |  | New Criteria
Application-Decommission | 2 |  | Impact to Other Systems | Value | Implementation Coordination Complexity | Value | Technical Change Experience | Value | Implementation Coordination Complexity (External) | Value
Application-Migration | 3 |  | None, or with 1 or more Productivity Critical systems | 1 | Requiring technical coordination involving 1-2 CIT work groups | 1 | Existing technology, with considerable experience | 1 | None, or with 1 Vendor | 1
Application-Patch | 4 |  | 1 to 2 Business or Mission Critical systems | 2 | Requiring technical coordination involving more than 2 CIT work groups | 2 | New technology, limited experience | 2 | Involving 2 Vendors | 2
Application-Provision | 5 |  | 3 or more Business or Mission Critical systems | 3 | Requiring technical and business coordination (e.g. business has to temporarily adjust their standard operating procedures) | 3 | New technology, no experience | 3 | Involving 3 or more Vendors | 3
Application-Upgrade | 6
Application-Modification | 7 |  | Impact to System & Service Availability | Value | Roll Back Effort | Value | Business Impact | Value
Critical_Facilities-Configuration | 1 |  | With or without system downtime but no service outage | 1 | Roll back plan in place and easily executed and with no Service Outage | 1 | None | 0
Critical_Facilities-Decomission | 2 |  | With service outage less than one hour | 2 | Roll back possible, though not easily executed or with Service Outage | 2 | Financial | 5 |  | Yes / No / N/A
Critical_Facilities-Preventive Maintenance | 3 |  | With service outage more than one hour | 3 | Roll back difficult, impossible or undesirable or with Service Outage | 3 | Legal/Regulatory | 5 | Yes / No / Intermittent | Yes
Critical_Facilities-Provision | 4 | [5 empty] | Financial & Legal/Regulatory | 5 | Service is down | No
Critical_Facilities-Upgrade | 5 |  | Project / BAU |  | Driver |  |  |  | Service is intermittent or degraded | N/A
Critical_Facilities-Modification | 6 |  | Project |  | Business |  | Yes / No |  | No service disruption
Database-Backup | 1 |  | BAU |  | Technology / CIT |  | Yes
Database-Configuration | 2 |  | Operational Initiative (OI) |  |  |  | No
Database-Decommission | 3 |  | Security Risk Criteria | [5 empty] | Groups | Full Name
Database-Migration | 4 | [5 empty] | LMH | Value | Cybersecurity | Cybersecurity
Database-Upgrade | 5 | [5 empty] | Low | 1 | SDO-AS | SDO-Application Services
Database-Modification | 6 | [5 empty] | Medium | 2 | SDO-Core | SDO-Core Network
Firewall-Configuration | 1 | [5 empty] | High | 3 | SDO-EUS | SDO-End User Services
Firewall-Decommission | 2 |  | Skill Level | Value | Loss of confidentiality | Value | Please fill out Security Tab: | 0 | SDO-SMM | SDO-Systems Management and Monitoring
Firewall-Preventive Maintenance | 3 |  | Security Penetration Skills | 9 | Minimal non-sensitive data disclosed | 2 |  |  | SDO-SOC | SDO-Security Operations
Firewall-Provision | 4 |  | Network and Programming Skills | 6 | Minimal critical data disclosed | 6 | Q1 | Value | SDO-IT Platforms | SDO-IT Platforms Administration
Firewall-Upgrade | 5 |  | Advanced Computer Users | 5 | Extensive non-sensitive data disclosed | 6 | Yes. It will require change on any of the following: Firewall, Active Directory, DNS, DHCP, System Center Configuration Manager, Patch link, Intrusion Prevention System, Virtual Private Network (VPN). | 2 | EIA | Enterprise ICT Architecture
Firewall-Modification | 6 |  | Some Technicak Skills | 3 | Extensive critical data disclosed | 7 | Yes. It will require change on any of the following: Volume Activation Management Tool, McAfee, Symantec for Sharepoint, Ironport, Airwatch, Digital certificates, Microsoft Bitlocker (MBAM) , Intune, Microsoft Enterprise Mobility Suite, Nessus Vulnerability Assessment Tool, AV , Secure Web Gateway, Wireless IPS (WIPS). | 1 | SolDel-CMS | SolDel-Customer Management Solutions
Network_Access-Configuration | 3 | Routing for wireless LAN at Business; Vlan segmentation for MOC; configuration of dual link for Pagbilao; PARCS Frequency Configuration | No Technical Skills | 1 | All data disclosed | 9 | No. It will not require change on any existing Security tool. | 0 | SolDel-CorpSol | SolDel-Corporate Solutions
Network_Access-Decommission | 5 | Replacement of LAN switches at Sectors | [6 empty] | SolDel-EDMS | SolDel-EDMS
Network_Access-Preventive Maintenance | 1 | Holy week preventive maintenance. Tetra preventive maintenance. No change in config | Motive | Value |  |  | Q2 | Value | SolDel-SS | SolDel-Shared Services
Network_Access-Provision | 3 | Installation of new AMIIS collector/ cpe Base station; Installation of new router for business center. | Low or No Reward | 1 | Loss of integrity | Value | Yes. It will require modification on the existing privilege accounts or creation of new privilege access. | 2 | Tel-Access | Telecoms Access Network
Network_Access-Upgrade | 5 | Change of cisco 6750 to 6850 at MOC. Replacement of LAN switches at Sectors | Possible Reward | 4 | Minimal slightly corrupt data | 1 | No. It will require access modification but will not entail privilege access. | 0 | Tel-ICT FM | Telecoms ICT Facilities Management
Network_Access-Modification | 0 |  | High Reward | 9 | Minimal seriously corrupt data | 3 | No. It has no impact at all on user access or privilege account. | 0 | Tel-Transport | Telecoms Transport Network
Network_Core-Configuration | 1 |  |  |  | Extensive slightly corrupt data | 5 | Q3 | Value
Network_Core-Decommission | 2 |  | OPPORTUNITY | Value | Extensive seriously corrupt data | 7 | Yes. The change will involve disclosure of confidential information. | 2
Network_Core-Preventive Maintenance | 3 |  | Full Access or Expensive Resources Required | 0 | All data totally corrupt | 9 | No. The change will not involve disclosure of confidential information. | 0 | LMH | Value
Network_Core-Provision | 4 |  | Special Access or Resources Required | 4 |  |  |  |  | Low | 1
Network_Core-Upgrade | 5 |  | Some Access or Some Resources Required | 7 | Loss of availability | Value | Q4 | Value | Medium | 2
Network_Core-Modification | 6 |  | No Access or No Resources Required | 9 | Minimal secondary services interrupted | 1 | Yes, this will result to new service definition to our Service Catalogue. | 1 | High | 3
Network_Transport-Configuration | 5 | Reroute Data link for Pagbilao/ Transfer of Malaya_Teresa & Duhat_Novaliches from existing Freq. to new Freq |  |  | Minimal primary services interrupted | 5 | No. Service already exists in our Service Catalogue. | 0
Network_Transport-Decommission | 5 | Decommissioning of Alcatel 7500 | SIZE | Value | Extensive secondary services interrupted | 5
Network_Transport-Preventive Maintenance | 1 | Holy week preventive maintenance. No change in config | Developers | 2 | Extensive primary services interrupted | 7 | Q5 | Value
Network_Transport-Provision | 3 | (data link) Provision of data link/ route for new Business Center/ ADMS CPE/ Tetra link/ PARCS base station/ Wireless LAN link/ Voice VLAN link; (new MPLS node) *no historical yet. | System Administrators | 2 | All services completely lost | 9 | The system is currently not exposed. Change will expose it. | 2
Network_Transport-Upgrade | 5 | Upgrade of MPLS Upgrade of Kamagong ASR IOS Version from 4.2.3 to 5.3.3. | Intranet Users | 4 |  |  | The system is currently exposed. Modification is required on current settings. | 1
Network_Transport-Modification | 0 |  | Partners | 5 | Loss of accountability | Value | The system is currently exposed. Modification is not required on current settings | 0
Security_Tools-Configuration | 3 | Configuration of Active Diretory | Authenticated Users | 6 | Fully traceable | 1 | The system is not and will not be exposed to the Internet. | 0
Security_Tools-Decommission | 1 | Decommissioning of SIEM | Anonymous Internet Users | 9 | Possibly traceable | 7
Security_Tools-Preventive Maintenance | 1 | *no historical |  |  | Completely anonymous | 9
Security_Tools-Provision | 0 | ?
Security_Tools-Migration | 0 | *no historical yet.
Security_Tools-Upgrade | 5 | New windows OS Patch for Workstation / Servers; Patch updates for McAfee
Security_Tools-Modification | 0
Server-Backup | 1 |  | Risk | Value | Fix
Server-Configuration | 2 |  | Accept | 1 | Yes, Rework
Server-Decommission | 3 |  | Mitigate | 2 | Yes, New Issue
Server-Migration | 4 |  | Transfer | 3 | No
Server-Preventive Maintenance | 5
Server-Provision | 6
Server-Upgrade | 7
Server-Modification | 8
Storage-Backup | 1
Storage-Configuration | 2
Storage-Decommission | 3
Storage-Migration | 4
Storage-Preventive Maintenance | 5
Storage-Provision | 6
Storage-Upgrade | 7
Storage-Modification | 8
Telephony-Configuration | 3 | Configuration CUCM;
Telephony-Decommission | 3 | Replacement of Legacy Telephony
Telephony-Preventive Maintenance | 3 | Holy week preventive maintenance
Telephony-Provision | 5 | installation new VG; installation of CUCM
Telephony-Upgrade | 5
Telephony-Modification | 0
Tetra-Configuration | 3 | Configuration of dual link for Tetra Base Station
Tetra-Decommission | 3 | *historical yet
Tetra-Preventive Maintenance | 1 | Preventive maintenance of TBS
Tetra-Provision | 3 | *historical yet
Tetra-Upgrade | 5 | TNX patch upgrade; Base station Upgrade.
Tetra-Modification | 0
Others-Please Specify | 8
5 –higher chance of encountering an issue
1 – lowest chance of encountering an issue

## RC (hidden)
Risk Calculator |  |  | Category |  | Risk Calculator w/ Sec |  |  | Category
Impact to Other Systems | None, or with 1 or more Productivity Critical systems | 1 | Low | 7 | Impact to Other Systems | None, or with 1 or more Productivity Critical systems | 1 | Low | 7
Impact to System & Service Availability | With service outage less than one hour | 2 | Medium | 8-14 | Impact to System & Service Availability | With service outage less than one hour | 2 | Medium | 8-14
Implementation Coordination Complexity | Requiring technical coordination involving 1-2 CIT work groups | 1 | High | 15 | Implementation Coordination Complexity | Requiring technical coordination involving 1-2 CIT work groups | 1 | High | 15
Implementation Coordination Complexity (external) | None, or with 1 Vendor | 1 |  |  | Implementation Coordination Complexity (external) | None, or with 1 Vendor | 1
Roll Back Effort | Roll back plan in place and easily executed and with no Service Outage | 1 |  |  | Roll Back Effort | Roll back plan in place and easily executed and with no Service Outage | 1
Technical Change Experience | Existing technology, with considerable experience | 1 |  |  | Technical Change Experience | Existing technology, with considerable experience | 1
Business Impact | Financial | 5 |  |  | Business Impact | Financial | 5
Risk | MEDIUM | 12 |  |  | Sec. | LOW | 1
[5 empty] | Risk | MEDIUM | 13
Error Message for Calculator: | Please fill out all information below:
Security Risk Calculator |  |  | Category
1 | No. It will not require change on any existing Security tool. | 0 | Low | 3
2 | No. It has no impact at all on user access or privilege account. | 0 | Medium | 4-6
3 | No. The change will not involve disclosure of confidential information. | 0 | High | 7
4 | No. Service already exists in our Service Catalogue. | 0
5 | The system is currently exposed. Modification is required on current settings. | 1
Risk | LOW | 1
Error Message for Calculator: | Please fill out Security Tab:

## Log (hidden)
Revision History SERVICE TRANSITION MANAGEMENT
Document Information
Rev. No. | Description of Change | Author | Reviewed and Approved By | Date
1 | Initial Version | Edlyn Aspacio / Juan Paulo Rodriguez | Genolyn Paraiso | 2017-02-08
2 | Updated the tabs, corrected formula, removed repetitive fields such as Planned Start and End Dates etc |  | Genolyn Paraiso | 2018-10-18
MERALCO CONFIDENTIAL End of Page 1

## Change Type and Sub-Type Data (hidden)
Application | Critical_Facilities | Database | Firewall | Network_Access | Network_Core | Network_Transport | Security_Tools | Server | Storage | Telephony | Tetra | Others
Configuration | Configuration | Backup | Configuration | Configuration | Configuration | Configuration | Configuration | Backup | Backup | Configuration | Configuration | Please Specify
Decommission | Decommission | Configuration | Decommission | Decommission | Decommission | Decommission | Decommission | Configuration | Configuration | Decommission | Decommission
Migration | Preventive Maintenance | Decommission | Preventive Maintenance | Preventive Maintenance | Preventive Maintenance | Preventive Maintenance | Preventive Maintenance | Decommission | Decommission | Preventive Maintenance | Preventive Maintenance
Patch | Provision | Migration | Provision | Provision | Provision | Provision | Provision | Migration | Migration | Provision | Provision
Provision | Upgrade | Upgrade | Upgrade | Upgrade | Upgrade | Upgrade | Migration | Preventive Maintenance | Preventive Maintenance | Upgrade | Upgrade
Upgrade | Modification | Modification | Modification | Modification | Modification | Modification | Upgrade | Provision | Provision | Modification | Modification
Modification | Others | Others | Others | Others | Others | Others | Modification | Upgrade | Upgrade | Others | Others
Others | [6 empty] | Others | Modification | Modification
[8 empty] | Others | Others

## Guide
Change and Release Plan Guide SERVICE TRANSITION MANAGEMENT | [6 empty] | FR-7.4-001 Rev. Code: 0
1. STM Guidelines
1.1 Quick Guide
1. File the Change in CITSM and fill out all fields marked with "*". Ensure that "Target Date" field is accurate and up to date and status is set to "For CAB Approval".
2. Stand alone / Mother RFC scenarios. a) IF this Change and Release Plan is for a Stand Alone RFC, accomplish all tabs as necessary. b) IF this Change and Release Plan is for a Mother RFC and child RFCs are under a SINGLE Change Owner Group. A Change and Release Plan will be created per System/Equipment and all changes will be summarized under one Change and Release Plan. If there are multiple changes to a single System/Equipment there is no need to create a Change and Release Plan for each child RFC. c) IF this Change and Release Plan is for a Mother RFC and child RFCs are shared among MULTIPLE Change Owner Groups. Change and Release Plan will be created for the Mother RFC which will be maintained by the Change Owner Group who is requesting support for their initiative. A Change and Release Plan will be created per System/Equipment and all changes will be summarized under one Change and Release Plan. ***Ensure that RFCs are linked properly in CITSM***
3. For Firewall Policy RFCs, fill out the "Firewall Policy Change and Release Plan"
4. Release Checklist a) Ensure that all items in the Release Checklist have been declared if applicable or not. b) Ensure that all the required artifacts are embedded in the Release Checklist tab or attached in CITSM.
5. Create the Release Notification and RFC Business Impact Acceptance form as aligned with the CITSM data.
6. Take note of the cut off time. Should the RFC be filed after the cut off time and there is a need to expedite the RFC Send an email to : Service Transition Management <group.service.transition.management@meralco.com.ph> Stating the Reason why the RFC needs to be expedited: Allowable reasons: - Financial impact - Legal/regulatory impact - Security impact - Business operational impact (non P1/P2) - Oversight (e.g. lack of planning)
7. Service Transition Management will be reviewing all documents that are included in the cut off and inform you of any lacking documents. If you have provided all necessary documents, you will receive an invite to discuss the RFC further in a PreCAB session. Please ensure that the Change Owner is present or represented.
8. After PreCAB, all open items must be accomplished before being endorsed to CAB.
9. Service Transition Management will notify you once your change has been reviewed and endorsed by CAB.
10. After the Hypercare period (Default 10 days), ensure that the Post Implementation Evaluation (PIE) Form has been accomplished in the RFC ticket in CITSM Service Transition Management should be informed should any issues arise during deployment, or if any issues arise that are related to the RFC.
For more information on the process you may refer to the following process manuals: a) Technical Change Management b) Release and Deployment Management c) Configuration Management
1.2 General Terms
Field |  | Description
RFC |  | A record containing the details of a change. Each change record documents the lifecycle of a single change. An RFC is created for every proposed change request. RFCs are stored in the CIT Service Manager (CITSM).
Mother RFC |  | An RFC record that is used to bundle together multiple changes that share a single objective.
Change Owner |  | The Change Owner is the owner of the configuration item affected by the change request. The Change Owner is accountable for the completing the requirements of the RFC as it goes through the RFC lifecycle, and for the successful implementation and subsequent closure of the record; and responsible for the accuracy and quality of the RFC and ensuring that it adheres to all relevant process controls. Other responsibilities include the following: • Confirm the requested change is feasible. • Prepare the required key documents specific to their domain: Change and Release plan (which includes the deployment plan, post-implementation tests, and rollback plan). • Confirm that schedule is acceptable, and sufficient, competent resource is available to support the implementation and any post-implementation activities. • Ensure change goes through quality checks and other clearances. • Ensure all affected Configuration Items (CI) are defined and changes to attributes and relationships documented. • Represent the RFC specific to their domain at relevant assessment discussions and Change Advisory Board (CAB). • Ensure that change implemented is within the stated change scope and the change window. • Provide feedback on the progress of the change activity until completion, and elevate/escalate any issues encountered for proper action to the Change Requestor, Technical Change Management team, and other relevant stakeholders or groups involved. • Close the RFC ticket on time after change implementation with complete Post Implementation Evaluation and other applicable documentations.
Change Requestor (ICT) |  | The person who initially perceives the need for a change and executes the steps necessary to meet the initial requirements for a Request for Change (RFC). This may be an end-user, process caretaker or internal to ICT. Key responsibilities of the Change Requestor: • File the change as soon as the need is identified. • Complete the initial RFC details. Completing as much information on the change as possible (this includes the Background, Change justification, Scope, Benefits among others). • For multiple interdependent RFCs, file the other interrelated RFCs and completing the initial RFC details. • Coordinate the requirements and collaborate with Change Owners of other interdependent work streams, support teams, and the business representatives to bring the solution together. • Secure agreement from and notify all affected stakeholders on planned start and end times for the change • Represent the RFCs, with a holistic view of all the associated changes, at relevant assessment discussions and Change Advisory Board (CAB) • Once initial RFC details have been completed, the Product Owner of the domain affected shall assume the role of the non-ICT change requestor.
Release Owner |  | • Prepare and complete Release Checklist & Release Package prior to deployment • Escalate issues or problems during Release Package development to stakeholders • Develop the deployment and rollback procedures • Monitor progress of releases during deployment • Send out timely communication to stakeholders related to release progress, status and expectations • Comply with the OATC requirements
CAB |  | The Change Advisory Board (CAB) is a body that authorizes changes based on assessment and prioritization of changes. When a CAB is convened, members are chosen to ensure that all changes within the scope of the CAB are adequately assessed from both a business and a technical viewpoint. The CAB shall recommend the adoption or rejection of changes appropriate for higher-level authorization and recommendations will be submitted to the appropriate change authority. Other stakeholders may be invited as resource persons as required.
Configuration Item |  | An ICT component in use in production or non-production environment that needs to be controlled and managed in order to deliver an ICT service.
CI Owner |  | • Ensure all CIs are registered in CMDB with the appropriate status and configuration data. • Validate that CI modifications resulting from RFCs implemented are reflected in the CMDB. • Overall accountable for their CI data quality and completeness in the CMDB. • Work with Configuration Management team to identify root causes and implement corrections for any discrepancies identified. • For non-production environment and End-User Services, the CI owner will be accountable and responsible in updating CI attributes and relationships.
Product Owner |  | Refers to the organization responsible for the end-to-end product life cycle Refers to the organization responsible for defining and developing a specific service or set of services of a product and their component service offerings.
Service Owner |  | Refers to the organization / team that has overall, end-to-end responsibility for delivering, maintaining, and decommissioning a specific service or set of services of a product and their component service offerings.
Product |  | Refers to applications / system solutions that are developed/acquired to support business needs.
Service |  | Refers to product offerings or activities provided to a customer to attain business objectives.
Asset Owner |  | Refers to the organization responsible for purchase, build, implement, operate and maintenance of the asset.
1.3 RFC Approval & Lead Time
Change Model | Description |  | Risk Level | Approver | Lead Time - PreCAB to Implementation | PreCAB Frequency | Cut-Off for PreCAB inclusion
Standard | A pre-approved change that is generally low risk and follows a procedure or work instruction (Request Fulfillment). Standard changes are pre-defined and listed as part of the standard changes appendix in the Request Fulfillment process. |  | Low | Pre-approved | Follows RF | N/A | N/A
Normal | Normal change is a non-standard change. It requires an RFC and shall follow the complete change management process. Expedited RFC is a Normal Change but does not follow the usual lead time. It is a means to accommodate time-sensitive but non-emergency changes. Allowable reasons: - Financial impact - Legal/regulatory impact - Security impact - Business operations impact - Oversight Needs supporting evidence. Pre-approval from the Group Head of the Change Requestor must be secured before TCM will process the request. |  | Low | Immediate Manager of the Change Owner and STM Manager | 1 Day | MON to FRI 2:30PM onwards | 10AM of same day as PreCAB
|  |  | Medium | CAB | 2 Days | TUE & THU 10AM – 12NN | 2 days after PreCAB (THU onwards or SAT onwards)
|  |  | High | CAB | 3 Days | TUE only 10 am – 12 noon | 3 days after PreCAB (FRI onwards)
Emergency | Emergency change is an unplanned change that requires immediate action to restore or prevent service disruption and has a high level of business and service impact. This is applicable for P1/P2 incidents. |  | Medium / High | ECAB | N/A | Anytime | N/A
2. Tab Guide & Description
2.1 Release Checklist
Allt should be filled up for all Changes/RFCs. All items should be accomplished. Change / Release Owners are responsible for filling this out. Please note that all items should be fulfilled for before this will be endorsed for PreCAB.
2.2 Change Plan
2.2.1 Change Details
Field |  | Description
RFC Number |  | RFC number copied from CITSM
RFC Title |  | RFC Title copied from CITSM.
System / Equipment Name |  | System name of the system where the Change will be applied to. If this is a new application, note this by appending "NEW" to the System Name field.
System Classification |  | Identify the System classification that will be affected by the change to be implemented. You may select "Other" if System Classification cannot be identified.
Change Type |  | Identify the type of the change to be implemented. You may select "Other" if Change type cannot be identified.
Fix |  | Select "Yes" if the RFC is related to a fix. "Rework" if this is related to a previous RFC and "New Issue" if this is the first time the issue has been brought up. If this is a totally new RFC, select "No".
Project / BAU / OI |  | Select "Project" if the change is related to or in support of a Project. Select "BAU" if this is a business operational activity. Select "OI" if driven by an Operational Initiave.
2.2.2 Risk Calculator
The Risk Calculator is used to compute the Total Risk Level of a non-standard change. This is composed of 2 parts, General Change Details and Security Risk. These are all dropdown fields, select what is applicable to your change. All fields need to be filled out before Total Risk Level will compute.
General Change Details
Field |  | Description
Impact to Other Systems |  | Refers to the Impact of the Change to other systems, this does not include the system where the Change is being applied to. Example Scenario: System A & B are connected and are both Mission Critical. - If RFC will only affect System A. There is no Impact to Other Systems. Select the option "None, or with 1 or more Productivity Critical systems". - If RFC will affect how System A communicates to System B. Select the option "1 to 2 Business or Mission Critical systems". - If RFC affects multiple systems each with different criticality, it should be based on the higher one. Order from highest to lowest is Mission Critical, Business Critical, Productivity Critical, Function Specific.
Impact to System & Service Availability | No | This refers to the impact on System and Service Availability. Refer to "Service Downtime" & "System Downtime" definition in 2.1.3 Change Schedule
Internal Implementation Coordination Complexity | No | Refers to the number of ICT groups that the Change Requestor (ICT) and/or Change Owner has to coordinate with to implement the Change. Change Requestor (ICT) and/or Change Owner's group should be included in the count. Governing groups not included (Cybersecurity, STM, QPA etc.)
External Implementation Coordination Complexity |  | Refers to the number of external groups (Vendor) that the Change Owner has to coordinate with to implement the Change.
Roll Back Effort | No | Difficulty of restoring the system to its previous state
Technical Change Experience | In place, easily executed | Refers to how experienced and familiar the Change Owner is with the Change to be implemented.
With Financial or Regulatory Exposure | In place, easily executed | Identify if this change is done for regulatory compliance, and/or will result to any financial impact if not met.
Security Risk
Field |  | Description
Does the change require modification of existing Security tool? |  | There are 2 sets of Security Tools listed, select which one is applicable. If Change will not involve any Security Tools select "None". There should be no occurrence where the Change will affect 2 or more Security Tools, this should be separate RFCs.
Does the change require modification on user access or provision of privilege account? |  | Identify if there will be any modifications on Access Management. If there is, determine if the change has to do with privilege account. User Access refers to who or what can use resources in the production environment.
Does the change involve disclosure of confidential information including personal information to external parties (outside of Meralco)? |  | Identify if there will be any disclosure of confidential information.
Will the change result to a new service? |  | You may refer to the Service Catalogue in CITSM for a consolidated list of Services.
Exposure of the system to the internet |  | Refers to the specific change being applied to the system only.
2.2.3 Risk Management (For High Risk Changes Only)
Column |  | Description
Risk Event |  | An uncertain event or condition that, if it occurs, has a positive or negative effect on the objectives of the Change.
Probability |  | A measure of how likely an individual risk is to occur (Low/Medium/High)
Potential Impact |  | A measure of the effect of a risk on one or more objectives if it occurs
Response |  | Defines the set of actions which most enhance the chances of success. • Accept – risk was recognized but no additional action will be performed to address the risk; • Mitigate – certain actions will be implemented to lower the probability or impact of the risk; • Transfer – transference to a third party that is better positioned to address a particular risk;
Action |  | Actions to be taken for the particular risk
Action Owner |  | The person responsible for ensuring that an appropriate response strategy is selected and implemented, and for determining suitable risk actions to implement the chosen strategy, with each risk action assigned to a single risk action owner.
2.2.4 Topology
You may attach or provide the repository location. Change Impact on the Physical or Technical Topology, before and after state.
2.3 Deployment and Backout Plan
The Deployment and Backout Plan is used by the Deployment Team during implementation. This is crafted by the Change / Release Owner. Change / Release Owner may also provide an MoP in lieu of filling up the Deployment and Backout Plan. All activities that have input into the Deployment and Backout Plan should be in the Change Window, should an activity be done outside the Change Window such as testing it should be indicated in the Remarks column. Attach or note the location of: • MoP • Post Implementation Test Scenarios (if not yet captured in the MOP or Section C. POST IMPLEMENTATION ACTIVITIES)
Field |  | Description
RFC |  | RFC number is taken from the Change Plan tab if populated
RFC Title |  | RFC Title is taken from the Change Plan tab if populated
A. PRE-IMPLEMENTATION ACTIVITIES (Not included in the Change Window) |  | Activities that should be done before Implementation, such as setups and testing should be stated here. This is NOT included in the Change Window. If the “pre-activity” stated is modifying any existing production system / equipment it should be documented in the During Implementation Activities instead.
B. DURING IMPLEMENTATION ACTIVITIES |  | Activities to be done during Implementation should be stated here.
C. POST IMPLEMENTATION ACTIVITIES |  | Steps to be taken after implementation should be stated here. The actual Post-Implementation test scenarios may be indicated here or as a separate attachment.
D. BACK-OUT PLAN |  | Steps to be taken should an issue be encountered, should be stated here.
E. ADDITIONAL ATTACHMENTS |  | Note the repository location or attach the artifacts in this section.
Activity |  | Name of the Activity.
Start Time |  | Start time per activity.
End Time |  | End time per activity.
Responsible Person |  | Person responsible for accomplishing the activity and notifying the escalation officer.
Responsible Group |  | ICT Group of the person responsible for accomplishing the activity and notifying the escalation officer.
Success Criteria |  | What will be the criteria for success to proceed to the next activity, you may populate this field for critical / testing activities.
If Failed, Proceed to Step.. |  | Indicate which activity should be done should an activity fail to meet the stated Success Criteria.
Remarks |  | Additional Column for remarks. Should the deployment cross into the next day you may note it here.
2.4 CMDB Update Form
FOR CHANGES IN RELATIONSHIP AND CI TEMPLATE CREATION OR MODIFICATION For New CI Template: Go to “Create New CI Template” tab. For Modification of CI Template: Choose the appropriate tab and insert the attributes to add / modify below. TO ADD/MODIFY CI ATTRIBUTES Step 1: Use the appropriate template to input attributes and relationships Step 2: Fill-up the required fields per tab such as: RFC Number - RFC number is taken from the Change Plan tab if populated Reference ID Select from the dropdown list if "New CI" or "Update CI" Step 3: If New CI: Fill-up the required fields (include optional fields if necessary). If Update CI: Input the current and new value of the attribute(s) and relationships to be updated.
2.5 Email Notification - Forms
The Release Notifications consists the Release Notification and Business Acceptance. The Release Notification is to be sent to all stakeholders via email to inform them that the activity is starting. Business Acceptance is to be sent to Process Caretakers/Application Administrators/Business Project Manager/CTAT Business Partners/Business Users to seek approval on the impact of the change that will be implemented consisting the details of service disruption and duration

## 1. Release Checklist
| RELEASE CHECKLIST SERVICE TRANSITION MANAGEMENT |  |  | FR-7.4-001 Rev. Code: 0
RFC # |  | RFC629598
RFC TITLE |  | CXE Release 5B - 5.1.0
Please fill out the checklist below with either "Yes" or "N/A". Do not leave any item unanswered. Please attach artifacts in CITSM or embed within this checklist. Note: Embedding is allowed for overall Change & Release Plan file size not exceeding 5MB. |  |  |  | 9
You may promote ticket status to 'For CAB Approval'
ITEM |  |  | ARTIFACT PROVIDED? (Yes, N/A) | REMARKS
GENERAL
Change and Release Plan Has the file been accomplished? |  |  | Yes
CMDB Update Has the CMDB Update form been filled out? (Required for changes in CI attributes or CI template) |  |  | Yes
IT QPA Endorsement Has this RFC been endorsed by IT QPA? (Exceptions: firewall configuration, server provisioning and Telecoms changes) |  |  | Yes | Embed email here or attach in CITSM.
Operations Group Acceptance Has Operations Group/s acknowledged via email their involvement in/support for the deployment of the change? |  |  | N/A | Embed email here or attach in CITSM.
Cybersecurity Endorsement Has this RFC been endorsed by Cybersecurity Team? Note: Please refer to "Cybersec Scope" tab |  |  | N/A | Embed email here or attach in CITSM.
Business Acceptance Have you secured business acceptance for the planned change implementation? Required for: - Service-Affecting changes (intermittence/degradation/downtime) - Changes to User Interfaces regardless of service impact |  |  | Yes | Embed email here or attach in CITSM.
SDO - SMM Acknowledgement Has the change been acknowledged by SMM team? (Required for changes related to IP Telephony, New applications/solutions, Data Network topology changes - change in IP Address, Site/Location assignment, Port/Interface Equipment) |  |  | N/A | Embed email here or attach in CITSM.
ADDITIONAL for APPLICATION CHANGES ONLY
Release Notes Does the change require application versioning? If yes, fill out release notes |  |  | Yes | Embed file here or attach in CITSM.
Program Transfer Sheet (Production) Has the PTS-P been accomplished specifying the final objects to be deployed in production? |  |  | Yes | Embed file here or attach in CITSM.
MERALCO CONFIDENTIAL End of Page 1

## 2. Change Plan
| CHANGE PLAN SERVICE TRANSITION MANAGEMENT |  |  |  | FR-7.4-001 Rev. Code: 0
A. CHANGE DETAILS
RFC Number | RFC629598 | RFC Title | CXE Release 5B - 5.1.0
System / Equipment Name | CXE | System Classification | Application | Change Type | Modification
|  | Project / BAU / OI | BAU | Is this a Fix? | No
D. RISK CALCULATOR (To be filled out by Change Owner)
Total Risk Level |  | MEDIUM
Impact to Other Systems |  | None, or with 1 or more Productivity Critical systems |  |  |  | 0 | 0
Impact to System & Service Availability |  | With service outage less than one hour |  |  |  | 0 | 0
Internal Implementation Coordination Complexity |  | Requiring technical coordination involving 1-2 CIT work groups |  |  |  | 0 | No | In place, easily executed
External Implementation Coordination Complexity |  | None, or with 1 Vendor
Roll Back Effort | No | Roll back plan in place and easily executed and with no Service Outage |  |  |  | #REF!
Technical Change Experience | In place, easily executed | Existing technology, with considerable experience |  |  |  | #REF! | #REF! | #REF!
With Financial or Regulatory Exposure | In place, easily executed | Financial |  |  |  | #REF! | #REF! | #REF!
Security Risk
Does the change require modification of existing Security tool? |  | No. It will not require change on any existing Security tool.
Does the change require modification on user access or provision of privilege account? |  | No. It has no impact at all on user access or privilege account.
Does the change involve disclosure of confidential information including personal information to external parties (outside of Meralco)? |  | No. The change will not involve disclosure of confidential information.
Will the change result to a new service? |  | No. Service already exists in our Service Catalogue.
Exposure of the system to the internet |  | The system is currently exposed. Modification is required on current settings.
E. RISK MANAGEMENT (For High Risk Changes Only)
Risk Event | Probability (Low, Medium, High) | Potential Impact (Low, Medium, High) | Response (Accept, Mitigate, Transfer) | Action | Action Owner
F. TOPOLOGY / SOLUTION ARCHITECHTURE (Required for Infrastructure / Data Interfaces / Network connectivity changes)

## 3. Deployment & Backout Plan
|  | DEPLOYMENT AND BACK-OUT PLAN SERVICE TRANSITION MANAGEMENT | [7 empty] | FR-7.4-001 Rev. Code: 0
RFC # |  | RFC629598
RFC Title |  | CXE Release 5B - 5.1.0
CHANGE IMPLEMENTATION ACTIVITIES
Fill out all sections. If not required, indicate the reason or justification.
Activity |  |  | Start Time | End Time | Responsible Person | Responsible Group | Success Criteria | If Failed, Proceed to Step.. | Remarks
A. PRE-IMPLEMENTATION ACTIVITIES (Not included in the Change Window)
A Technical Deploment Plan
A1 | Get the approval from Meralco / CIT to start Pre-Implementation Activities (covers:change set preparations, pre-deployment activities) |  | Thur 04/23/20 9:00 AM | Thur 04/23/20 5:00 PM | Nate | Meralco
B | Pre-Implementation Activities
SFDC
B1.1 | Provide component list for 5B+Security (Lot 2) components in excel format |  | Mon 04/20/20 9:30 AM | Mon 04/20/20 6:30 PM | Satyajit | Capgemini
B1.2 | Prepare and Review final component /configuration List |  | Tue 04/21/20 9:30 AM | Tue 04/21/20 6:30 PM | Anant / Satyajit | Capgemini
B1.3 | Prepare new Changset in FUAT Enviornment |  | Wed 04/22/20 9:00 AM | Wed 04/22/20 5:00 PM | Satyajit | Capgemini
B1.4 | Upload Change Sets from FUAT to Prod |  | Wed 04/22/20 5:00 PM | Wed 04/22/20 7:00 PM | Satyajit | Capgemini
B1.5 | Validate & Resolve any Changset Issues |  | Thur 04/23/20 9:00 AM | Thur 04/23/20 7:00 PM | Anant / Satyajit | Capgemini
B1.6 | Buffer Window (to fix any Test coverage & Changeset issues) |  | Fri 04/24/20 9:00 AM | Fri 04/24/20 12:00 PM | Anant / Satyajit | Capgemini
B1.7 | Create a new Sandbox as Prod Backup |  | Fri 04/24/20 9:00 AM | Fri 04/24/20 01:00 PM | Sid / Nate | Capgemini / Meralco
B1.8 | Provide access to CG for newly created Sandbox |  | Fri 04/24/20 01:00 PM | Fri 04/24/20 02:00 PM | Sid / Nate | Capgemini / Meralco
B1.9 | CG to confirm access to Sandbox |  | Fri 04/24/20 02:00 PM | Fri 04/24/20 03:00 PM | Montosh / Satyajit | Capgemini
Marketing Cloud
B2.1 | Backup Journeys/Automation Scripts |  | Fri 04/24/20 09:00 AM | Fri 04/24/20 12:00 PM | Vamshi/Abhishek/Montosh | Capgemini
B2.2. | Monitor the daily sync up process (Bill note) |  | Fri 04/24/20 09:30 AM | Fri 04/24/20 10:30 AM | Vamshi/Abhishek/Montosh | Capgemini
B2.3 | Provide API keys for journeys to Heroku |  | Fri 04/24/20 12:00 PM | Fri 04/24/20 01:00 PM | Vamshi/Abhishek/Montosh | Capgemini
Heroku
B3.1 | Initialize the Config Variables |  | Fri 04/24/20 09:00 AM | Fri 04/24/20 12:00 PM | Supriyo / Ken | Capgemini
B3.2 | Back up the code /configurations |  | Fri 04/24/20 12:00 PM | Fri 04/24/20 03:00 PM | Supriyo / Ken | Capgemini
B3.3 | Code Comparison between FUAT and Prod |  | Fri 04/24/20 12:00 PM | Fri 04/24/20 03:00 PM | Supriyo / Ken | Capgemini
B3.4 | Heroku DB Scripts Readiness |  | Fri 04/24/20 09:00 AM | Fri 04/24/20 12:00 PM | Supriyo / Ken | Capgemini
B3.5 | Monitor the daily sync up process (Bill note) |  | Fri 04/24/20 09:30 PM | Fri 04/24/20 10:30 PM | Supriyo / Ken | Capgemini
Mobile
B4.1 | Get the APK signing key and ensure that key is used for last play store release.(Andriod) |  | Tue 04/21/20 9:00 AM | Tue 04/21/20 9:15 AM | Prashant | Capgemini
B4.2 | Get the IOS application’s p12 key, signing certificate and provisioning profile.(Ios) |  | Tue 04/21/20 9:15 AM | Tue 04/21/20 9:30 AM | Prashant | Capgemini
B4.3 | Update the APP_ENV for customer login from Environment.FUAT to Environment.PROD in configuration.ts. 1. Validate Community Portal URL in environment.service.ts. 2. Get connected APP Endpoint URL of Production from Production Org. 3.Cross check the SFDC co |  | Tue 04/21/20 9:30 AM | Tue 04/21/20 12:30 PM | Akshay / Prashant | Capgemini
B4.4 | Check the existing permissions are not obsoleted due to the API level change. |  | Tue 04/21/20 9:30 AM | Tue 04/21/20 12:30 PM | Akshay / Prashant | Capgemini
B4.5 | Ensure the correct app icons are added to “AndroidManifest.xml” and res folder in Salesforce SDK dir. |  | Tue 04/21/20 9:30 AM | Tue 04/21/20 12:30 PM | Akshay / Prashant | Capgemini
B4.6 | Update the google-services.json from uat to prod |  | Tue 04/21/20 9:30 AM | Tue 04/21/20 12:30 PM | Akshay / Prashant | Capgemini
C. DURING IMPLEMENTATION ACTIVITIES
Mobile
C1.1 | Change the app bundle identifier to com.meralco.phone.move in config.xml, package.json and package-lock.json. Ensure the specific platforms are updated with changed app bundle identifier. |  | Tue 04/21/20 12:30 PM | Tue 04/21/20 2:30 PM | Akshay / Prashant | Capgemini
C1.2 | Change the app bundle identifier to com.meralco.moveiphone in xcode general settings.xml for IOS. |  | Tue 04/21/20 12:30 PM | Tue 04/21/20 2:30 PM | Akshay / Prashant | Capgemini
C1.3 | Confirm and update the app version number for both the platforms from Meralco. |  | Tue 04/21/20 12:30 PM | Tue 04/21/20 2:30 PM | Akshay / Prashant | Capgemini
C1.4 | Confirm the “minSdkVersion” and “targetSdkVersion“ for android and “deployment-target” for IOS from Meralco; which should be configured in config.xml. And ensure the platform specific configuration files are updated. |  | Tue 04/21/20 12:30 PM | Tue 04/21/20 2:30 PM | Akshay / Prashant | Capgemini
C1.5 | Ensure the correct app icons are added to “AndroidManifest.xml” and res folder in Salesforce SDK dir. |  | Tue 04/21/20 12:30 PM | Tue 04/21/20 2:30 PM | Akshay / Prashant | Capgemini
C1.6 | Ensure the correct application icons are added in the application's “assets -> icons” configuration for IOS. |  | Tue 04/21/20 12:30 PM | Tue 04/21/20 2:30 PM | Akshay / Prashant | Capgemini
C1.7 | Update the permissions in AndroidManifest.xml |  | Tue 04/21/20 12:30 PM | Tue 04/21/20 2:30 PM | Akshay / Prashant | Capgemini
C1.8 | Add the Appsflyer configuration in AndroidManifest.xml |  | Tue 04/21/20 12:30 PM | Tue 04/21/20 2:30 PM | Akshay / Prashant | Capgemini
C1.9 | Confirm the GCM Sender id, application identifier and access token from Marketing Cloud team for Push Notifications and ensure the config.xml updated with the production details. |  | Tue 04/21/20 12:30 PM | Tue 04/21/20 2:30 PM | Akshay / Prashant | Capgemini
C1.10 | Validate the IPA file using the apple pre-validation tool and ensure there is no warnings and errors. |  | Tue 04/21/20 12:30 PM | Tue 04/21/20 2:30 PM | Akshay / Prashant | Capgemini
C1.11 | Validate the APK file and ensure it signed using the google key. |  | Tue 04/21/20 12:30 PM | Tue 04/21/20 2:30 PM | Akshay / Prashant | Capgemini
C1.12 | Distribute the ios package from Xcode to Testflight |  | Tue 04/21/20 2:30 PM | Tue 04/21/20 3:30 PM | Akshay / Prashant | Capgemini
C1.13 | Configure Manual Release Option to "Yes" in Testflight |  | Wed 04/22/20 1:30 AM | Wed 04/22/20 2:30 AM | Brian | Meralco
C1.14 | Generate a signed apk if we have google play store signing key otherwise unsigned APK for android using Android Studio. (Have delivery the same to Meralco CIT Team) |  | Tue 04/21/20 2:30 PM | Tue 04/21/20 3:30 PM | Akshay / Prashant | Capgemini
C1.15 | Upload the Ios app for Apple validation and enable the manual release of the application. |  | Tue 04/21/20 6:00 PM | Tue 04/21/20 7:00 PM | Akshay / Prashant | Capgemini
C1.16 | Upload the APK for google validation and enable the manual release of the application. |  | Tue 04/21/20 6:00 PM | Tue 04/21/20 7:00 PM | Akshay / Prashant | Capgemini
C2 | Inform Call Center before turning-off the chatbot so that they can revert to native FB during the downtime |  | Fri 04/24/20 10:00 PM | Fri 04/24/20 10:30 PM |  | Meralco
C3 | Disable Chatbot system |  | Fri 04/24/20 10:30 PM | Fri 04/24/20 11:00 PM |  | Chatbot
C4 | Turn on the maintenance Page on Meralco Online Portal and Meralco Mobile App |  | Fri 04/24/20 11:00 PM | Fri 04/24/20 11:30 PM | Montosh / Prashant | Capgemini
C5 | Freeze the internal & External Salesforce users |  | Fri 04/24/20 11:30 PM | Sat 04/25/20 12:00 AM |  | Meralco
SFDC
C6.1 | Deploy the Change Set |  | Sat 04/25/20 12:00 AM | Sat 04/25/20 1:00 AM | Anant / Satyajit | Capgemini
C6.2 | Deploy Configuration Changes |  | Sat 04/25/20 1:00 AM | Sat 04/25/20 5:00 AM | Anant / Satyajit | Capgemini
C6.3 | Validate & Resolve any Changset Issues |  | Sat 04/25/20 5:00 AM | Sat 04/25/20 6:00 AM | Anant / Satyajit | Capgemini
Marketing Cloud
C7.1 | Implement Marketing Cloud Changes - Non Schema Changes |  | Sat 04/25/20 1:00 AM | Sat 04/25/20 5:00 AM | Montosh/Abhishek | Capgemini
C7.2 | Implement Marketing Cloud Changes - Schema Related Changes |  | Sat 04/25/20 1:00 AM | Sat 04/25/20 5:00 AM | Montosh/Abhishek | Capgemini
Heroku
C8.1 | Build & Deploy the Codes to Heroku Prod App |  | Sat 04/25/20 12:00 AM | Sat 04/25/20 3:00 AM | Supriyo / Ken | Capgemini
C8.2 | DB Schema Changes |  | Sat 04/25/20 12:00 AM | Sat 04/25/20 3:00 AM | Supriyo / Ken | Capgemini
IIB
C9.1 | Build & Deploy the Codes to IIB Prod App |  | Sat 04/25/20 12:00 AM | Sat 04/25/20 3:00 AM |  | IIB
C9.2 | Monitor Daily Sync up for additional data coming in Bills |  | Fri 04/24/20 8:30 PM | Sat 04/25/20 10:30 AM |  | IIB
CMS
C10.1 | Build & Deploy the Codes to CMS Prod App |  | Sat 04/25/20 1:00 AM | Sat 04/25/20 3:00 AM |  | CMS
C11 | Activate Cha, Mel, Gerlyn, Sids account for Smoke Testing purpose |  | Sat 04/25/20 6:00 AM | Sat 04/25/20 6:30 AM |  | Meralco
C12 | Turn off the maintenance Page on Meralco Online Portal and Meralco Mobile App |  | Sat 04/25/20 6:30 AM | Sat 04/25/20 7:00 AM | Montosh / Prashant | Capgemini
C13 | Turn on the Red Banner outside Meralco Online and update the content base on the copy provided by Marketing. |  | Sat 04/25/20 6:30 AM | Sat 04/25/20 7:00 AM | Montosh / Prashant | Capgemini
C14 | Turn on the Yellow Banner inside Meralco Online and update the content base on the copy provided by Marketing. |  | Sat 04/25/20 6:30 AM | Sat 04/25/20 7:00 AM | Montosh / Prashant | Capgemini
C15 | CG Smoke Testing & Fixing |  | Sat 04/25/20 7:00 AM | Sat 04/25/20 8:00 AM | Montosh / Prashant | Capgemini
D. POST IMPLEMENTATION ACTIVITIES (If no Test Scenarios are attached, detail the tests to be conducted and success criteria)
D1 | Coordinate with Business Teams for Smoke Testing for assigned person/s to start smoke test. Smoke Testing start and end time will depend on Business availability. |  | Sat 04/25/20 8:00 AM | Sat 04/25/20 12:00 PM |  | Meralco Business Teams
D2 | Cybersecurity Testing |  | Sat 04/25/20 8:00 AM | Sat 04/25/20 12:00 PM |  | Meralco Cyber sec
D3 | CG Team to provide extended ticket support for Business smoke testing |  | Sat 04/25/20 8:00 AM | Sat 04/25/20 1:00 PM | Satyajit / Montosh | Capgemini
D4 | Unfreeze internal & External Salesforce users |  | Sat 04/25/20 12:00 PM | Sat 04/25/20 1:00 PM |  | Meralco
D5 | Turn off the Red Banner outside Meralco Online and update the content base on the copy provided by Marketing. |  | Sat 04/25/20 1:00 PM | Sat 04/25/20 1:30 PM | Montosh / Prashant | Capgemini
D6 | Turn off the Yellow Banner inside Meralco Online and update the content base on the copy provided by Marketing. |  | Sat 04/25/20 1:00 PM | Sat 04/25/20 1:30 PM | Montosh / Prashant | Capgemini
D7 | Enable Chatbot system |  | Sat 04/25/20 1:30 PM | Sat 04/25/20 2:00 PM |  | Chatbot
D8 | Monitor SFMC Notifications |  | Sun 04/26/20 9:00 AM | Sun 04/26/20 6:00 PM |  | Meralco Business+CG Dev
SFDC
D9.1 | Capture the snapshot of Changes |  | Sat 04/25/20 5:00 AM | Sat 04/25/20 9:00 AM | Montosh / Anant | Capgemini
Marketing Cloud
D10.1 | Capture the snapshot of Changes |  | Sat 04/25/20 5:00 AM | Sat 04/25/20 6:00 AM | Montosh/Abhishek | Capgemini
D10.2 | Implement Marketing Cloud Changes - Schema Related Changes |  | Sat 04/25/20 1:00 PM | Sat 04/25/20 5:00 PM | Montosh/Abhishek | Capgemini
D10.3 | Monitor the data for Bill notes triggerred on Saturday |  | Sat 04/25/20 8:30 PM | Sat 04/25/20 10:30 PM | Montosh/Abhishek | Capgemini
Heroku
D11.1 | Capture the snapshot of Changes |  | Sat 04/25/20 3:00 AM | Sat 04/25/20 4:00 AM | Supriyo / Ken | Capgemini
D11.2 | Monitor the data for Bill notes triggerred on Saturday |  | Sat 04/25/20 8:30 PM | Sat 04/25/20 10:30 PM | Supriyo / Ken | Capgemini
Mobile
D12.1 | Capture the snapshot of Changes |  | Tue 04/21/20 3:30 PM | Tue 04/21/20 4:00 PM | Prashant | Capgemini
Mobile App Release
D14.1 | Release the Android build to end users. |  | Sat 04/25/20 2:00 PM | Sat 04/25/20 3:00 PM | Brian | Meralco
D14.2 | Release the iOS build to end users. |  | Sat 04/25/20 2:00 PM | Sat 04/25/20 3:00 PM | Brian | Meralco
D14.3 | Update the version number in custom settings for both Android & IOS |  | Sat 04/25/20 2:00 PM | Sat 04/25/20 3:00 PM | Brian | Meralco
D14.4 | Merge Master branch with Develop Branch (Code Merging) |  | Sat 04/25/20 3:00 PM | Sat 04/25/20 5:00 PM | Prashant | Capgemini
D14.5 | Delivery the production Source Code to MERALCO Team. |  | Sat 04/25/20 3:00 PM | Sat 04/25/20 5:00 PM | Prashant | Capgemini
E. BACK-OUT PLAN
E1 | Deploy Backup Change Sets / Components in PRD |  | Sat 04/25/20 12:00 PM | Sat 04/25/20 2:00 PM | Satyajit / Montosh | Capgemini
E2 | Confirm Completion of the Backout Plan |  | Sat 04/25/20 2:00 PM | Sat 04/25/20 3:00 PM | Satyajit / Montosh | Capgemini
E3 | Confirm success of the backout / sanity test after business testing |  | Sat 04/25/20 3:00 PM | Sat 04/25/20 3:15 PM | Satyajit / Montosh | Capgemini
E4 | If backout deployment is confirmed success, final step is to disable the Portal Banner for the CXE Downtime |  | Sat 04/25/20 3:15 PM | Sat 04/25/20 4:00 PM | Satyajit / Montosh | Capgemini
E. ADDITIONAL ATTACHMENTS
Attach or note the location of: MoP Post Implementation Test Scenarios (if not yet captured in the MOP or Section C. POST IMPLEMENTATION ACTIVITIES)

## Child RFCs (hidden)
| List of Children RFCs SERVICE TRANSITION MANAGEMENT | [6 empty] | FR-ICIO-439 Rev. Code: 2
Mother RFC | RFC629598
CHANGE IMPLEMENTATION RFCs
RFC Number | Fix | Planned Deployment Date | Responsible Person | Responsible Group | System Classification | Change Type | Scope | Remarks
1 | [8 empty] | - | #N/A
2 | [8 empty] | -
3 | [8 empty] | -
4 | [8 empty] | -
5 | [8 empty] | -
6 | [8 empty] | -
7 | [8 empty] | -
8 | [8 empty] | -
9 | [8 empty] | -
10 | [8 empty] | -
11 | [8 empty] | -
12 | [8 empty] | -
13 | [8 empty] | -
14 | [8 empty] | -
15 | [8 empty] | -
16 | [8 empty] | -
17 | [8 empty] | -
18 | [8 empty] | -
19 | [8 empty] | -
20 | [8 empty] | -
21 | [8 empty] | -
22 | [8 empty] | -
23 | [8 empty] | -
24 | [8 empty] | -
25 | [8 empty] | -

## Release Checklist (hidden)
|  | RELEASE CHECKLIST SERVICE TRANSITION MANAGEMENT |  |  |  | FR-ICIO-439 Rev. Code: 2
RFC # |  |  | RFC629598
RFC TITLE |  |  | CXE Release 5B - 5.1.0
Change/Release Owner |  |  | #REF!
Target START DATE & TTME |  |  | #REF!
Target END DATE & TIME |  |  | #REF!
Items declared as applicable should have a requisite artifact attached in CITSM
A. RELEASE CHECKLIST (PRE-ENDORSEMENT)
ITEM | CRITERIA DELIVERABLES |  |  | APPLICABLE? Declare all (Yes,No) | ARTIFACT PROVIDED IN REPOSITORY / CITSM? (Yes,No,N/A) | COMMENTS
1 | data Network Bandwidth Consumption Email Endorsement from Telecomms Transport, this is required for Enterprise Wide Deployment of an existing service / application.
2 | Release Notes For Application Only, you may refer to (TG-ICIO-311) for guidelines
3 | Business Acceptance Email acceptance of planned change implementation. 1. Service-Affecting changes 2. Changes to user interfaces (regardless if service or non-service affecting
4 | IT QPA Endorsement Endorsement from IT QPA (exceptions Telecoms)
5 | Program Transfer Sheet (Production) Accomplished Program Transfer Sheet, should contain all objects that will be deployed to production. (application only)
6 | Security Standards Compliance Email Endorsement from CTSA-CyberSecurity, required for but not limited to the ff: deployment of new applications/solutions, firewalls, security patching, new cloud solutions
7 | SDO - SOC Endorsement Email endorsement from SDO-SOC, required for firewall request for corporate users accessing ADMS Web app
8 | SDO - DBA Endorsement Email endorsement from SDO-DBA, this is required for but not limited to: new database for new application, additional database for an existing application, reuse of retired or active DB, upgrade or increase of DB server CPU, memory or related resources / change that will affect the BAU growth of the DB.
9 | SDO - CORE Network Endorsement Email Endorsement from SDO-Core Network, required for but not limited to the ff: Data transfer volume of more than 200gb via Network, new application/solution, new cloud solutions that will require bandwidth consumption
10 | Data Network Bandwidth Consumption Email Endorsement from Telecomms Transport, this is required for Enterprise Wide Deployment of an existing service / application.
11 | SDO - SMM Endorsement Email endorsement from SDO-SMM, this is required for but not limited to: IP Telephony, Data Network Changes in Topology (Change in IP Address, Site/Location assignment, Port/Interface Equipment)
12 | CMDB Update Refers to the CMDB update form that should be filled out and attached to the RFC in CITSM, this applies to all RFCs with CI updates
MERALCO CONFIDENTIAL End of Page 1

## 4. CMDB Update
CMDB UPDATE F SERVICE TRANSITION - CONFIGURATION MANAGEMENT | CMDB UPDATE FORM SERVICE TRANSITION MANAGEMENT | [5 empty] | FR-ICIO-444 Rev. Code: 0
| RFC # |  | RFC629598
| RFC Title |  | CXE Release 5B - 5.1.0
Select the CI type below and fill out the attributes to be updated.
For updating multiple CIs of the same type or other concerns, please contact STM for assistance.
CI TEMPLATES
CREATE NEW CI TEMPLATE
CREATE NEW CI TEMPLATE SERVICE TRANSITION - CONFIGURATION MANAGEMENT
RFC NUMBER
REFERENCE ID
| NEW CI OR UPDATE CI |  |  |  | Update CI |  |  | CI Linking/Relationships
| ATTRIBUTE |  |  |  | CURRENT VALUE (If the value is not on the drop-down list, indicate it in Remarks.) | NEW VALUE | REMARKS | CI Name | Link Type
CI Name
Full Name
CI Owner
Services
Criticality
Asset Lifecycle Status
Current State
LIST ATTRIBUTES TO CAPTURE
MERALCO CONFIDENTIAL
APPLICATION
CMDB UPDATE FORM - APPLICATION SERVICE TRANSITION - CONFIGURATION MANAGEMENT
REFERENCE ID
| NEW CI OR UPDATE CI | [6 empty] | CI Linking/Relationships
| ATTRIBUTE |  |  |  | CURRENT VALUE (If the value is not on the drop-down list, indicate it in Remarks.) | NEW VALUE | REMARKS | CI Name | Link Type
| CI Name |  |  |  | Salesforce | Salesforce
| Full Name |  |  |  | Salesforce - Sales, Service and Community | Salesforce - Sales, Service and Community
| CI Owner |  |  |  | CMS-SOLDEL | CMS-SOLDEL
| Latest Release Date |  |  |  | 2020-01-25 | 2020-02-05
| Latest Version |  |  |  | 2020.2.0.1 | 2020.2.0.2
App Version
Application Provider
Installer Source
| URL |  |  |  | https://meralco.my.salesforce.com | https://meralco.my.salesforce.com
Services
Development Platform
Development Tool
| Build |  |  |  | COTS | COTS
| Hosting Type |  |  |  | Cloud | Cloud
Primary Users
User Location
| Environment |  |  |  | Production | Production
| Criticality |  |  |  | Mission Critical | Mission Critical
Current State
LIST ATTRIBUTES TO CAPTURE
MERALCO CONFIDENTIAL
CLUSTER
CMDB UPDATE FORM - CLUSTER SERVICE TRANSITION - CONFIGURATION MANAGEMENT
REFERENCE ID
| NEW CI OR UPDATE CI | [6 empty] | CI Linking/Relationships
| ATTRIBUTE |  |  |  | CURRENT VALUE (If the value is not on the drop-down list, indicate it in Remarks.) | NEW VALUE | REMARKS | CI Name | Link Type
CI Name
CI Owner
Location
Asset Lifecycle Status
Current State
LIST ATTRIBUTES TO CAPTURE
MERALCO CONFIDENTIAL
OPERATING SYSTEM
CMDB UPDATE FORM - OPERATING SYSTEM SERVICE TRANSITION - CONFIGURATION MANAGEMENT
REFERENCE ID
| NEW CI OR UPDATE CI | [6 empty] | CI Linking/Relationships
| ATTRIBUTE |  |  |  | CURRENT VALUE (If the value is not on the drop-down list, indicate it in Remarks.) | NEW VALUE | REMARKS | CI Name | Link Type
CI Name
CI Owner
OS Architecture
Service Pack
Criticality
Asset Lifecycle Status
Current State
LIST ATTRIBUTES TO CAPTURE
MERALCO CONFIDENTIAL
SERVER
CMDB UPDATE FORM - SERVER SERVICE TRANSITION - CONFIGURATION MANAGEMENT
REFERENCE ID
| NEW CI OR UPDATE CI | [6 empty] | CI Linking/Relationships
| ATTRIBUTE |  |  |  | CURRENT VALUE (If the value is not on the drop-down list, indicate it in Remarks.) | NEW VALUE | REMARKS | CI Name | Link Type
CI Name
CI Owner
Company Number
Manufacturer
Model
Serial Number
Services
Hostname
Operating System
Processor
Memory
IP Address
Physical Server
VM Version
Storage Size
# of CPUs/Cores
Rack
Server Type
Server Patch Update Mode
Firmware Version
Location
Segment
Environment
Criticality
Asset Lifecycle Status
Current State
LIST ATTRIBUTES TO CAPTURE
MERALCO CONFIDENTIAL
STORAGE ARRAY
CMDB UPDATE FORM - STORAGE ARRAY SERVICE TRANSITION - CONFIGURATION MANAGEMENT
REFERENCE ID
| NEW CI OR UPDATE CI | [6 empty] | CI Linking/Relationships
| ATTRIBUTE |  |  |  | CURRENT VALUE (If the value is not on the drop-down list, indicate it in Remarks.) | NEW VALUE | REMARKS | CI Name | Link Type
CI Name
CI Owner
Company Number
Model
IP Address
Serial Number
Physical Capacity
Location
Row
Rack
Criticality
Asset Lifecycle Status
Current State
LIST ATTRIBUTES TO CAPTURE
MERALCO CONFIDENTIAL
DATABASE
CMDB UPDATE FORM - DATABASE SERVICE TRANSITION - CONFIGURATION MANAGEMENT
REFERENCE ID
| NEW CI OR UPDATE CI | [6 empty] | CI Linking/Relationships
| ATTRIBUTE |  |  |  | CURRENT VALUE (If the value is not on the drop-down list, indicate it in Remarks.) | NEW VALUE | REMARKS | CI Name | Link Type
CI Name
CI Owner
Host Server
DB Patch
Database Version
Database Edition
Services
Operating System
Hostname
IP Address
Total Database Memory
Processes
Sessions
Back Up Type
EM Enrollment
AWR Retention
Audit Log Retention
Database Type
DB Creation Date
Category
Location
Environment
Criticality
Asset Lifecycle Status
Current State
LIST ATTRIBUTES TO CAPTURE
MERALCO CONFIDENTIAL
APPLIANCE
CMDB UPDATE FORM - APPLIANCE SERVICE TRANSITION - CONFIGURATION MANAGEMENT
REFERENCE ID
| NEW CI OR UPDATE CI | [6 empty] | CI Linking/Relationships
| ATTRIBUTE |  |  |  | CURRENT VALUE (If the value is not on the drop-down list, indicate it in Remarks.) | NEW VALUE | REMARKS | CI Name | Link Type
CI Name
Full Name
CI Owner
Company Number
Serial Number
Latest Version
IP Address
Location
Services
Criticality
Asset Lifecycle Status
Current State
LIST ATTRIBUTES TO CAPTURE
MERALCO CONFIDENTIAL
FABRIC INTERCONNECT
CMDB UPDATE FORM - FABRIC INTERCONNECT SERVICE TRANSITION - CONFIGURATION MANAGEMENT
REFERENCE ID
| NEW CI OR UPDATE CI | [6 empty] | CI Linking/Relationships
| ATTRIBUTE |  |  |  | CURRENT VALUE (If the value is not on the drop-down list, indicate it in Remarks.) | NEW VALUE | REMARKS | CI Name | Link Type
CI Name
CI Owner
Company Number
Manufacturer
Classification
Serial Number
IP Address
Location
Services
Criticality
Asset Lifecycle Status
Current State
LIST ATTRIBUTES TO CAPTURE
MERALCO CONFIDENTIAL
LOAD BALANCER
CMDB UPDATE FORM - LOAD BALANCER SERVICE TRANSITION - CONFIGURATION MANAGEMENT
REFERENCE ID
| NEW CI OR UPDATE CI | [6 empty] | CI Linking/Relationships
| ATTRIBUTE |  |  |  | CURRENT VALUE (If the value is not on the drop-down list, indicate it in Remarks.) | NEW VALUE | REMARKS | CI Name | Link Type
CI Name
Full Name
CI Owner
Company Number
Manufacturer
Serial Number
Model
Services
IP Address
Software Version
Memory
Processor
Area
Location
Criticality
Asset Lifecycle Status
Current State
LIST ATTRIBUTES TO CAPTURE
MERALCO CONFIDENTIAL
ROUTER
CMDB UPDATE FORM - ROUTER SERVICE TRANSITION - CONFIGURATION MANAGEMENT
REFERENCE ID
| NEW CI OR UPDATE CI | [6 empty] | CI Linking/Relationships
| ATTRIBUTE |  |  |  | CURRENT VALUE (If the value is not on the drop-down list, indicate it in Remarks.) | NEW VALUE | REMARKS | CI Name | Link Type
CI Name
Full Name
CI Owner
Company Number
Classification
Manufacturer
Model
Serial Number
Services
IP Address
Software Version
Area
Location
Criticality
Asset Lifecycle Status
Current State
LIST ATTRIBUTES TO CAPTURE
MERALCO CONFIDENTIAL
FIREWALL
CMDB UPDATE FORM - FIREWALL SERVICE TRANSITION - CONFIGURATION MANAGEMENT
REFERENCE ID
| NEW CI OR UPDATE CI | [6 empty] | CI Linking/Relationships
| ATTRIBUTE |  |  |  | CURRENT VALUE (If the value is not on the drop-down list, indicate it in Remarks.) | NEW VALUE | REMARKS | CI Name | Link Type
CI Name
Full Name
CI Owner
Company Number
Manufacturer
Serial Number
Model
Services
IP Address
Software Version
Area
Location
Criticality
Asset Lifecycle Status
Current State
LIST ATTRIBUTES TO CAPTURE
MERALCO CONFIDENTIAL
SWITCH
CMDB UPDATE FORM - SWITCH SERVICE TRANSITION - CONFIGURATION MANAGEMENT
REFERENCE ID
| NEW CI OR UPDATE CI | [6 empty] | CI Linking/Relationships
| ATTRIBUTE |  |  |  | CURRENT VALUE (If the value is not on the drop-down list, indicate it in Remarks.) | NEW VALUE | REMARKS | CI Name | Link Type
CI Name
Full Name
CI Owner
Company Number
Model
Manufacturer
Classification
Serial Number
IP Address
Software Version
Area
Location
Criticality
Asset Lifecycle Status
Current State
LIST ATTRIBUTES TO CAPTURE
MERALCO CONFIDENTIAL
IP TELEPHONY SERVER
CMDB UPDATE FORM - IP TELEPHONY SERVER SERVICE TRANSITION - CONFIGURATION MANAGEMENT
REFERENCE ID
| NEW CI OR UPDATE CI | [6 empty] | CI Linking/Relationships
| ATTRIBUTE |  |  |  | CURRENT VALUE (If the value is not on the drop-down list, indicate it in Remarks.) | NEW VALUE | REMARKS | CI Name | Link Type
CI Name
CI Owner
Company Number
Services
IP Address
Hostname
Gateway
Location
Criticality
Asset Lifecycle Status
Current State
LIST ATTRIBUTES TO CAPTURE
MERALCO CONFIDENTIAL
PARCS BASE STATION
CMDB UPDATE FORM - PARCS BASE STATION SERVICE TRANSITION - CONFIGURATION MANAGEMENT
REFERENCE ID
| NEW CI OR UPDATE CI | [6 empty] | CI Linking/Relationships
| ATTRIBUTE |  |  |  | CURRENT VALUE (If the value is not on the drop-down list, indicate it in Remarks.) | NEW VALUE | REMARKS | CI Name | Link Type
CI Name
CI Owner
Company Number
Serial Number
Area
Model
Location
IP Address
Classification
Sector
Services
Lattitude
Longitude
Antenna Type
Antenna Height
Bandwidth
Tx Power
Basestation Frequency
Azimuth
Criticality
Asset Lifecycle Status
Current State
LIST ATTRIBUTES TO CAPTURE
MERALCO CONFIDENTIAL
TETRA BASE STATION
CMDB UPDATE FORM - TETRA BASE STATION SERVICE TRANSITION - CONFIGURATION MANAGEMENT
REFERENCE ID
| NEW CI OR UPDATE CI | [6 empty] | CI Linking/Relationships
| ATTRIBUTE |  |  |  | CURRENT VALUE (If the value is not on the drop-down list, indicate it in Remarks.) | NEW VALUE | REMARKS | CI Name | Link Type
CI Name
CI Owner
Company Number
Site Name
IP Address (1st)
IP Address (2nd)
Advantech EKI Switch
Serial Number
Manufacturer
Location
Services
Criticality
Asset Lifecycle Status
Current State
LIST ATTRIBUTES TO CAPTURE
MERALCO CONFIDENTIAL
TETRA NODE EXCHANGE
CMDB UPDATE FORM - TETRA NODE EXCHANGE SERVICE TRANSITION - CONFIGURATION MANAGEMENT
REFERENCE ID
| NEW CI OR UPDATE CI | [6 empty] | CI Linking/Relationships
| ATTRIBUTE |  |  |  | CURRENT VALUE (If the value is not on the drop-down list, indicate it in Remarks.) | NEW VALUE | REMARKS | CI Name | Link Type
CI Name
CI Owner
Equipment Type
Serial Number
Part Number
Services
Manufacturer
Model
Criticality
Asset Lifecycle Status
Current State
| LIST ATTRIBUTES TO CAPTURE | License Available | License Available | License Available
MERALCO CONFIDENTIAL
VOICE GATEWAY
CMDB UPDATE FORM - VOICE GATEWAY SERVICE TRANSITION - CONFIGURATION MANAGEMENT
REFERENCE ID
| NEW CI OR UPDATE CI | [6 empty] | CI Linking/Relationships
| ATTRIBUTE |  |  |  | CURRENT VALUE (If the value is not on the drop-down list, indicate it in Remarks.) | NEW VALUE | REMARKS | CI Name | Link Type
CI Name
CI Owner
Company Number
Location
Area
Protocol
IP Address
Domain
Serial No.
Manufacturer
Model
Equipment Location
E1 Port
Criticality
Asset Lifecycle Status
Current State
LIST ATTRIBUTES TO CAPTURE
MERALCO CONFIDENTIAL
VOICE LOGGER
CMDB UPDATE FORM - VOICE LOGGER SERVICE TRANSITION - CONFIGURATION MANAGEMENT
REFERENCE ID
| NEW CI OR UPDATE CI | [6 empty] | CI Linking/Relationships
| ATTRIBUTE |  |  |  | CURRENT VALUE (If the value is not on the drop-down list, indicate it in Remarks.) | NEW VALUE | REMARKS | CI Name | Link Type
CI Name
CI Owner
Company Number
Equipment Type
Services
Manufacturer
Model
Hostname
IP Address
Location
Criticality
Asset Lifecycle Status
Current State
LIST ATTRIBUTES TO CAPTURE
MERALCO CONFIDENTIAL
POWER SUPPLY
CMDB UPDATE FORM - POWER SUPPLY SERVICE TRANSITION - CONFIGURATION MANAGEMENT
REFERENCE ID
| NEW CI OR UPDATE CI | [6 empty] | CI Linking/Relationships
| ATTRIBUTE |  |  |  | CURRENT VALUE (If the value is not on the drop-down list, indicate it in Remarks.) | NEW VALUE | REMARKS | CI Name | Link Type
CI Name
CI Owner
Serial Number
Services
Location
Manufacturer
Model
Cost Center
Current
Criticality
Asset Lifecycle Status
Current State
LIST ATTRIBUTES TO CAPTURE
MERALCO CONFIDENTIAL

## 5. Release Notification
RELEASE NOTIFICATION
Please anticipate the following changes which will be moved to production pending approval.
RFC # | RFC629598
RFC TITLE | CXE Release 5B - 5.1.0
TARGET START DATE AND TIME
TARGET END DATE AND TIME
SERVICE IMPACT | No service disruption
DESCRIPTION OF CHANGES | <Paste from CITSM or free text>
CHANGE OWNER & IMPLEMENTING TEAM | <Paste from CITSM or free text>
DEPLOYMENT ACTIVITES | <free text>
Note:
Other STM-related forms to follow soon.

## 6. Cybersec Scope
CYBERSECURITY GUIDELINES ON TYPES OF CHANGES REQUIRING SECURITY ASSESSMENT
A. Changes Requiring Security Assessment
Change Type | Rationale | Illustrative Cases
Implementation of New Technologies • Cloud-based implementations • Implementation of new platforms, servers, databases systems, communications infrastructure | Assure that the security features of the new technology are enabled and optimized to reduce the risk of exposure Assure that the migration does not unduly expose the Meralco network, information and processes to unnecessary risks | • Implementation of applications on AWS, Azure, GCP, etc. • Implementation of PostGreSQL, hyperconverged infrastructure, network equipment, etc.
RFC’s under Major Projects | Ensure alignment with the design and the security objectives of the project, as developed with the participation of Cybersecurity Architecture | Examples • EAM RFC’s supporting the Priority Dashboard initiative • CXE-related changes • CTI-related changes • Acquisition of Telecoms equipment such as radio systems, network equipment, etc.
Cross-system integrations | Need to ensure that no undue risk is introduced by this system integration. Particular lookouts are • The integration is via secure protocols • The integrating systems have no outstanding major vulnerabilities • Cross-segment connections are duly managed with the use of DMZs | • Integration between OT and IT systems • Integrations with cloud systems or external parties
Application modifications with changes affecting the following: • Identity management (new roles, user registration) • Authentication (AD integration, logins) • Authorization (new system privileges) • Cryptography • Creation of new forms, objects, input fields • Session management (Cookies) • Business logic modifications which affect critical data or transactions (e.g. financial) | Leverage application testing tools, code reviews and code walkthroughs to minimize associated risks and to check that the change does not introduce application vulnerabilities to the system | • New interfaces to end users • New integrations to other systems • Upgrades that materially modify the overall composition of the system
Changes to security controls in place Ex. • firewall rules and segments • antivirus exceptions • deviations from agreed upon security controls • etc. | Understand the risks introduced by the change in security posture and implement possible mitigations | Antivirus exceptions
Changes that would result in external exposures | Understand the risks introduced by the change in security posture and implement possible mitigations | Access being given to non-Meralco, off-premise entities
B. Changes that Shouldn’t Go Through A Security Assessment
Type of Change | Rationale | Illustrative Cases
Patching | These are security best practices, and should be operational on the part of the asset owner.
Restarts | These are operational and should not affect the security posture of the system | • Server restarts • Wireless controller restarts • Network equipment restarts.
Minor modifications that do not materially alter the system, especially to not affect the security posture of the system. | The change is not expected to create new exposures and risks | • Minor changes entailing in-system object configurations • In system data handling • In system batch processing
Addition or removal of standard system components | Such components should follow the established controls for the initial deployment | • Addition of users within established roles • Expansion of network components such as domain controllers, meter collectors, etc.
Decommissioning | These actions will be covered by data sanitization procedures already established | Retirement of servers

## CMDB DATA (hidden)
ASSET LIFECYCLE STATUS | DEVELOPMENT TOOL | CURRENT STATE | CLASSIFICATION PARCS | CI LINKING
N/A | Eclipse | Defective | Base Station | Appliance
Acquired | J2EE | Deleted | Customer Premise Equipment (CPE) | Business Application
Deployed | J2ME | Donated |  | Cluster
Disposed | Java | For Assessment |  | Database
In Stock | Java Net | For Donation |  | Database Server
Retired | JSE | For Sale |  | ESX Host
| Lotus Notes | For Scrap |  | Firewall
| Maximo | For Verification |  | Mobile Application
| Microsoft .net | In Use |  | Peer
| Natural | Lost |  | Server
| Oracle BIEE | New Delivery |  | Storage Array
| PostGresql | On Loan |  | Switch
| Powerbuilder | Reserved |  | System (Host)
| Python | Scrapped |  | VM Server
| QT Creator | Service Unit |  | Web Application
| Tableau | Sold
CRITICALITY | Visual Studio | Standby
Mission Critical | X-code | Under Maintenance
Business Critical |  | Under Repair
Productivity Critical
Function Specific
PHYSICAL SERVER
Yes
No
SERVER TYPE
Application Server
Database Server
Proxy Server
Print Server
Web Server
FTP Server
File Server
Host
SERVER PATCH UPDATE MODE
N/A
Manual
SCCM
HOSTING TYPE
On-Premise
Appliance / Equipment-Based
Cloud
Hybrid
CLASSIFICATION
Edge
Industrial
Core (Transport)
Core (SDO)
DATABASE TYPE
ADABAS
MSQL
Oracle
Others
OS ARCHITECTURE
N/A
32-Bit
64-Bit
SERVICE PACK
N/A
0
1
2
AREA
Central
Corporate
North
South
Unspecified
MAINFRAME
Linux
Windows
MAC
BUILD
N/A
Non COTS
COTS
DEVELOPMENT PLATFORM
Mainframe
Linux
Windows
Mac
24/7
7am-7pm, Mon-Sun
7am-5pm, Mon-Sat
8am-5pm, Mon-Fri
LOCATION
N/A
DCCI
Lopez Server Farm
Old Data Center
DR Site
Ortigas
Balintawak
GDC
ODC
Alabang Business Center
Alabang Service Center
Metropolis Business Center Extension
Argono Business Center
Bacoor Business Center
Baliwag Business Center
Balagtas Business Center
Batangas Business Center
Balintawak Business Center
Balintawak District 1 (Admin)
Camarin Auxilary Business Center
Cavite District Office
Calamba Business Center
Cainta Business Center
Commonwealth Business Center
Dasmariñas Business Center
España Business Center
General Mariano Alvarez Business Center Extension
Caloocan Auxiliary Business Center
Kamuning Business Center
Lucena Business Center
Las Piñas Business Center
Los Baños Business Center Extension
Mandaluyong Business Center
Marikina Business Center
Makati Business Center
Manila District Office
Malabon Business Center
Malolos Business Center
Malate Business Center
Masinag Auxiliart Business Center
Novaliches Business Center
Plaridel District Office
Parañaque Auxiliary Business Center
Pasig Business Center
Pasig District Office
Pasay Auxiliary Business Center
Rizal District Office
Rosario Business Center
Roosevelt Business Center
San Miguel Business Center Extension
San Pablo Business Center
San Pablo District Office
San Pedro Business Center
Sta. Rosa District Office
Sta. Cruz Auxiliary Business Center
Sta. Maria Business Center
Trece Martirez Business Center Extension
Taguig Business Center Extension
Tagaytay Auxiliary Business Center Extension
Tanay Business Center Extension
Tutuban Business Center
Valenzuela Business Center
Valenzuela District Office
PDC
SDC
APPLICATION PROVIDER
Play Store
App Store
Microsoft Store
App Store and Play Store
All
MS Intune
HOSTING TYPE
On-premise
Cloud
Hybrid
Appliance/Equipment-based
ENVIRONMENT
Production
Non Production (Development, Test & QA)
USER LOCATION
Internal
Internal and External
CURRENT
AC
DC